## Sheet1
Project : Arvi [Web Development]
Platform : Web Portal/Admin (Angular)
Sr. no. | Milestones | Task Type | Task | Hours | Milestone Hours | Notes
Project Kick start task
| Milestone 1 | Front End (Web App) | GitHub Setup, Project structure, Server Setup in local | 8 | 40
|  |  | UI/Ux Design | 32
| Milestone 2 | Front End (Web App) | Login For all roles | 8 | 36
|  |  | Forgot Password | 8
|  |  | Profile, Change Password | 8
|  |  | Dashboard | 12
| Milestone 3 | Front End (Web App) | Plan Management | 16 | 48
|  |  | Coupon management | 16
|  |  | User management | 16
| Milestone 4 | Front End (Web App) | Customer Management | 16 | 42 | Service timelines is not part of this phase
|  |  | Subscription Management | 16
|  |  | View service timelines | 10
| Milestone 5 | Front End (Web App) | Create payment links | 12 | 74 | Payment link creation - we will push it to next phase
|  |  | View emergency dashboard | 12
|  |  | Add senior details | 10
|  |  | Add device details | 10 |  | Booking services is not part of this phase
|  |  | Book services | 16
|  |  | Testing | 14
Develoment Hours |  |  |  |  | 240
Total Project Hours |  |  |  |  | 240